## Sheet1
REDESIGN HOMEPAGE AND CHANNEL
| Module | Related files | Estimate time (day) | Owner | Number of Files | Status | Note
Homepage |  | redesign/tl_homepage.* (A) metaHeadStyle.tmpl (U) globalHeader.tmpl (U) breadcrumb.tmpl globalFooter.tmpl metaHead.tmpl /cm/youandyourweddinguk/site_images/redesign/redesignLeftLogo.png (N) /cm/youandyourweddinguk/site_images/redesign/redesignLeftLogoBottom.png (N) | 1 | Kieu Nguyen | 9
| Header + Navigation | redesignGlobal.css (A) /cm/youandyourweddinguk/site_images/redesign/bgLoginBox.png (A) /cm/youandyourweddinguk/site_images/redesign/bgSubMenu.png (A) | 2 | Kieu Nguyen | 3 | done
| Promoplayer | xs_uk_markup_promo_player_v3.tmpl (U) | 0.5 | Man Tran | 1 | done | modified old promo
| Slider | /redesign/moduleSlider.* (A) /cm/youandyourweddinguk/site_images/tool_scroller/ (A) (11 files) metaHeadScript.tmpl(U) /scripts/jquery.easing.1.3.js (A) /scripts/jquery.bxSlider.js (A) /scripts/jquery.bxSlider.min.js (A) | 1.5 | Man Tran | 17 | done | 1 PO for HP + 1 control article + 1 DTD + 7 PO for channel pages + RAW assets
| Latest Article | /redesign/moduleLatestArticle.* (A) /redesign/moduleLatestArticleItem.* (A) /cm/youandyourweddinguk/site_images/redesign/bg_title.png (A) | 1.5 | Man Tran | 5 | done | reuse 1 PO of HP + 7 PO for channel pages + 1 Cat(exist)
| Latest Gallery | /redesign/moduleLatestGallery.* (A) /redesign/moduleLatestGalleryItem.* (A) | 1.5 | Tuyet Huynh | 4 | done | create 7 PO for only channel page
| Editorial Control | moduleSponsorShip.* moduleSponsorShipItem.* | 1.5 | Tuyet Huynh | 4 | done | create 1 PO for HP + 2PO for channel + 1 Control Article + 1 DTD
| Global Right Rail | globalRightRail.tmpl top_nav.tmpl xs_uk_login_links.tmpl redesignRightRail.css adprecision.css moduleJoinUs.tmpl module_polls.tmpl module_latestforum.tmpl module_adprecision.tmpl module_competition.tmpl module_promotion.tmpl userBlogsAboutAuthor.tmpl userBlogsLatestBlogger.tmpl flipbookVersion2.css sweepsLanding.css wedsimple_uk.css community.css searchResults.css flipbookV1_5.css (U) quiz-abc-uk.css article.css searchResults.css epicBanner.css epicLanding.css web_search.css userBlogs.css | 2 | Kieu Nguyen | 26
Channel |  | redesign/tl_channel.* (A) redesignChannel.css | 1 | Kieu Nguyen | 3
| Static Promo | redesign/moduleSectionPromo.* (A) | 1.5 | Tuyet Huynh | 2 | done | 7 PO + 7 Control Articles + 1 DTD
| Bridal Basics | redesign/moduleBridalBasics.* (A) | 1.5 | Man Tran | 2 | done | 7 PO + Cat (note guidance to QC control )
76

## Control Article
ID | Public URL | Module | Name
6080103 | control-article-yywuk-tool-scroller-receptions | Slider | YYWUK - Tool Scroller
6080102 | control-article-yywuk-tool-scroller-real-weddings | Slider | YYWUK - Tool Scroller
6080095 | control-article-yywuk-tool-scroller-honeymoons | Slider | YYWUK - Tool Scroller
6079282 | control-article-yywuk-tool-scroller-gifts | Slider | YYWUK - Tool Scroller
6079281 | control-article-yywuk-tool-scroller-fashion | Slider | YYWUK - Tool Scroller
6079280 | control-article-yywuk-tool-scroller-beauty | Slider | YYWUK - Tool Scroller
6079269 | control-article-yywuk-tool-scroller-planning | Slider | YYWUK - Tool Scroller
6054763 | control-article-yywuk-tool-scroller-home | Slider | YYWUK - Tool Scroller
6085208 | control-article-yyw-static-promo-fashion | static promo player | moduleSectionPromo
6085075 | control-article-yyw-static-promo-beauty | static promo player | moduleSectionPromo
6091441 | control-article-yyw-static-promo-planning | static promo player | moduleSectionPromo
6091443 | control-article-yyw-static-promo-real-weddings | static promo player | moduleSectionPromo
6091444 | control-article-yyw-static-promo-receptions | static promo player | moduleSectionPromo
6091450 | control-article-yyw-static-promo-gifts | static promo player | moduleSectionPromo
6091457 | control-article-yyw-static-promo-gifts-honeymoons | static promo player | moduleSectionPromo
6059141 | control-article-yywuk-yyw-bride-candy | Editorial Control | moduleSponsorShip
6115611 | control-article-yywuk-yyw-bride-candy-beauty | Editorial Control | moduleSponsorShip
6115604 | control-article-yywuk-yyw-bride-candy-fashion | Editorial Control | moduleSponsorShip
6095923 | test-bridal-basic-01 | Bridal Basics | moduleBridalBasics.tmpl
6095934 | test-bridal-basic-02 | Bridal Basics | moduleBridalBasics.tmpl
6096668 | test-bridal-basic-03 | Bridal Basics | moduleBridalBasics.tmpl
6096670 | test-bridal-basic-04 | Bridal Basics | moduleBridalBasics.tmpl

## Page Objects
| ID | Public URL | Module | Name | Column1
| 10487 | PO_YYWUK_LATEST_GALLERIES_BEAUTY | Latest Gallery | moduleLatestGallery
| 10488 | PO_YYWUK_LATEST_GALLERIES_FASHION | Latest Gallery | moduleLatestGallery
| 10489 | PO_YYWUK_LATEST_GALLERIES_GIFTS | Latest Gallery | moduleLatestGallery
| 10490 | PO_YYWUK_LATEST_GALLERIES_PLANNING | Latest Gallery | moduleLatestGallery
| 10491 | PO_YYWUK_LATEST_GALLERIES_RECEPTIONS | Latest Gallery | moduleLatestGallery
| 10492 | PO_YYWUK_LATEST_GALLERIES_REAL_WEDDINGS | Latest Gallery | moduleLatestGallery
| 10493 | PO_YYWUK_LATEST_GALLERIES_HONEYMOONS | Latest Gallery | moduleLatestGallery
seuse | 7777 | PO_YYWUK_LATEST_GALLERIES | Latest Gallery | moduleLatestGallery | update Content Types: remove FB1.5; add FB2
| 10460 | PO_YYW_SPONSOR | Editorial Control | moduleSponsorShip
| 10472 | PO_YYW_SPONSOR_FASHION | Editorial Control | moduleSponsorShip
| 10473 | PO_YYW_SPONSOR_BEAUTY | Editorial Control | moduleSponsorShip
| 10624 | PO_YYW_PROMO_PLAYER_BEAUTY | Static Promo | moduleSectionPromo
| 10625 | PO_YYW_PROMO_PLAYER_FASHION | Static Promo | moduleSectionPromo
| 10626 | PO_YYW_PROMO_PLAYER_HONEYMOONS | Static Promo | moduleSectionPromo
| 10627 | PO_YYW_PROMO_PLAYER_GIFTS | Static Promo | moduleSectionPromo
| 10628 | PO_YYW_PROMO_PLAYER_PLANNING | Static Promo | moduleSectionPromo
| 10629 | PO_YYW_PROMO_PLAYER_REAL_WEDDINGS | Static Promo | moduleSectionPromo
| 10630 | PO_YYW_PROMO_PLAYER_RECEPTIONS | Static Promo | moduleSectionPromo
|  | PO_YYWUK_TODAY_HIGHLIGHTS | Latest Article | moduleLatestArticle
|  | PO_YYWUK_TODAY_HIGHLIGHTS_HONEYMOONS | Latest Article | moduleLatestArticle
|  | PO_YYWUK_TODAY_HIGHLIGHTS_BEAUTY | Latest Article | moduleLatestArticle
|  | PO_YYWUK_TODAY_HIGHLIGHTS_FASHION | Latest Article | moduleLatestArticle
|  | PO_YYWUK_TODAY_HIGHLIGHTS_GIFTS | Latest Article | moduleLatestArticle
|  | PO_YYWUK_TODAY_HIGHLIGHTS_PLANNING | Latest Article | moduleLatestArticle
|  | PO_YYWUK_TODAY_HIGHLIGHTS_REAL_WEDDINGS | Latest Article | moduleLatestArticle
|  | PO_YYWUK_TODAY_HIGHLIGHTS_RECEPTIONS | Latest Article | moduleLatestArticle

## Article Types
ID | Public URL | Module | Name
1363 | YYW - Static Promo Player | Static Promo | moduleSectionPromo
1360 | YYW - Sponsorship | Editorial Control | moduleSponsorShip

## Categories
ID | Category Name | Module | Name
3808 | YYW Homepage - Sponsorship | Editorial Control | moduleSponsorShip